## Roadmap
Salesforce architecture roadmap
Tucario working template. Rows 10–12 are fictional examples. Replace them before using the register for a real program.
Sequence is a dependency order, not a delivery commitment. Replace role labels with accountable names and agree acceptance evidence.
20 prepared entry rows (10–29). For more rows, extend the table, formulas, validation, conditional formatting and summary ranges.
ID | Business outcome | Decision / question | Evidence / status | Dependency IDs | Accountable owner | Next action | Acceptance evidence | Sequence / status
EX-R1 | Reduce inconsistent account reporting | Which system owns customer identity? | Illustrative: duplicate customer keys reported; sample reconciliation pending | None | Data owner | Compare source identifiers; agree authority and merge rules | Signed field-ownership map and reconciled sample | 1 / Investigate
EX-R2 | Make failed order messages recoverable | How will failed messages be replayed safely? | Illustrative: recovery steps undocumented; behavior needs test | EX-R1 | Integration owner | Test failure, retry and duplicate-message handling in a test environment | Replay test preserves order identity and alerts the agreed owner | 2 / Proposed
EX-R3 | Expand service without exposing records | Which groups need access to which records? | Illustrative: access requirements await business approval | EX-R1 | Service owner | Review access matrix and test allowed and denied cases | Approved access matrix and representative user tests | 3 / Proposed
How to use: record the business outcome, unresolved decision and evidence first. Link dependencies by ID; do not use dates to hide unresolved prerequisites.
Reference: Salesforce roadmap diagrams. Examples and template structure are editorial illustrations by Tucario.
https://architect.salesforce.com/docs/architect/reference-diagrams/guide/section-roadmap.html

## Debt Register
Salesforce technical debt register
Illustrative examples only. Replace rows 10–12. Amber cells are editable; blue-tinted Index cells calculate from the evidence state and scores.
Index is an optional discussion aid, not a Salesforce health score. Urgent security, privacy or service risks follow incident/escalation processes regardless of index.
20 prepared entry rows (10–29). For more rows, extend the table, formulas, validation, conditional formatting and summary ranges.
Recorded findings | 3 | Unknown evidence | 1 | Urgent, not closed | 1
ID | Finding | Evidence / date | Evidence state | Impact 1–3 | Likelihood 1–3 | Index | Urgent? | Owner | Next action | Effort | Status | Acceptance evidence | Dependency IDs
EX-D1 | Duplicate order created after message replay | Fictional test log: duplicate replay reproduced. Replace with your dated evidence. | Observed | 3 | 3 | 9 | No | Integration owner | Add/review idempotency; repeat replay test | Estimate pending | Open | Repeated message produces one business order | EX-R1
EX-D2 | Fields appear empty in a sample | Fictional limited sample. Dependency, integration and retention checks not yet performed. | Unknown |  |  | Needs evidence | No | Data owner | Check references and usage before any deletion | Investigation | Open | Documented dependencies and owner-approved disposition | None
EX-D3 | Test user can access restricted customer records | Fictional access test: access exceeds approved role. Replace with your dated evidence. | Observed | 3 | 2 | 6 | Yes | Security owner | Escalate under access incident process; contain and investigate | Assess urgently | In progress | Allowed/denied tests pass and owner accepts remediation | None
Suggested scales: agree these locally before scoring. Blank or invalid scores never calculate as zero. Unknown evidence requires investigation.
Impact: 1 = contained workaround; 2 = material process disruption; 3 = critical business, service or security consequence.
Likelihood: 1 = credible but unobserved in representative tests; 2 = evidenced plausible under expected change/load; 3 = recurring or confirmed trigger.
Scores express relative judgments, not probabilities. Within a category, use business context and dependencies before effort to decide the next action.
Reference: Salesforce Well-Architected. This workbook and its scoring suggestions are Tucario editorial examples, not a vendor standard.
https://architect.salesforce.com/docs/architect/well-architected/guide/framework.html